## Start Here
The 90-Day AI Rollout Runbook
AEGITz ¦ Phoenix's Business Resilience Partner ¦ aegitz.com
What this is for
A week-by-week sequence for putting AI into a business of roughly 30 to 80 people. The order matters more than the tool choice. Rollouts fail because they start with licenses instead of with an inventory and a policy.
How to use it
1. Work top to bottom on the Checklist tab. The order is deliberate.
2. Set Status on each line. The Progress tab totals as you go.
3. Put a real name in Owner. Unowned items do not get done.
4. Anything you mark N/A gets a reason in the Notes column.
Legend
Shaded cells are the ones you fill in.
Status options: Not started, In progress, Done, N/A.
This workbook is provided free by AEGITz. It is operational guidance, not legal advice. Have counsel review anything you adopt that carries a regulatory obligation.

## Checklist
# | Section | Task | Why it matters / how to do it | Status | Owner | Due | Notes
1 | Weeks 1 to 3: discover | Export every third-party app with an OAuth grant against your tenant | Entra > Enterprise applications, or Workspace > API controls. Look for anything with mail, file, or calendar access. | Not started
2 | Weeks 1 to 3: discover | Run an anonymous staff survey on current AI tool use | Five questions. Promise no consequences and mean it. Punishing honest answers buys six months of hidden usage. | Not started
3 | Weeks 1 to 3: discover | List the three most expensive repetitive tasks in the business | Most expensive, not most annoying. Hours multiplied by loaded labor rate. | Not started
4 | Weeks 1 to 3: discover | Measure a real baseline for the target task | Two weeks of actual logged time, not estimates. Estimates are wrong by about 30 percent in either direction. | Not started
5 | Weeks 1 to 3: discover | Check whether your data is ready | Run the AEGITz Data Readiness Audit. Under 60 percent means fix data before buying licenses. | Not started
6 | Weeks 4 to 6: govern | Draft a two-page acceptable use policy | Approved tools, the never list, the review requirement, disclosure rules, and how to request a new tool. | Not started
7 | Weeks 4 to 6: govern | Decide your data boundary | Commit to tools with contractual no-training terms and enterprise data handling. Block or discourage the consumer versions. | Not started
8 | Weeks 4 to 6: govern | Name a reviewer for each category of AI-assisted output | A role, not a general expectation. When something goes wrong, the difference between a mistake and negligence is often whether a review step existed. | Not started
9 | Weeks 4 to 6: govern | Run vendor due diligence on the tools you intend to buy | Use the AEGITz AI Vendor Security Questionnaire. Your insurer will ask for this file at renewal. | Not started
10 | Weeks 4 to 6: govern | Route the policy through handbook acknowledgment | A policy nobody signs is a draft. Re-acknowledge annually. | Not started
11 | Weeks 4 to 6: govern | Spend 15 minutes at an all-hands on the never list with two real examples | Context beats page count. | Not started
12 | Weeks 7 to 9: pilot | Pick one department with repetitive, reviewable work | Proposal and intake work in professional services. Submittals and RFIs in construction. Prior authorization in healthcare admin. | Not started
13 | Weeks 7 to 9: pilot | Audit permissions on everything the assistant will index | If you do one technical task, do this one. AI makes existing over-permissioning queryable in plain language. | Not started
14 | Weeks 7 to 9: pilot | Provision licenses for the pilot group only | Company-wide rollout hits the whole learning curve at once and produces a mutiny. | Not started
15 | Weeks 7 to 9: pilot | Deliver two hours of live training | Live, with your own documents, not a vendor webinar. | Not started
16 | Weeks 7 to 9: pilot | Name an owner for the experiment | One person accountable for the result. | Not started
17 | Weeks 7 to 9: pilot | Log hours weekly in the same place | Memory is a terrible measurement instrument. By week 12 everyone remembers it going better than it did. | Not started
18 | Weeks 10 to 13: decide | Discard the first two weeks of pilot data | That is the learning curve. Including it makes the tool look worse than it is. | Not started
19 | Weeks 10 to 13: decide | Calculate the result honestly | Use the AEGITz AI ROI Calculator. Time saved is not money saved unless it is billed, avoids a hire, or reduces spend. | Not started
20 | Weeks 10 to 13: decide | Apply the go or no-go criteria | If you cannot state a real number, buy fewer licenses, not more. | Not started
21 | Weeks 10 to 13: decide | Document what did not work and why | The failed workflows are more useful than the successful ones for choosing the next candidate. | Not started
22 | Weeks 10 to 13: decide | Expand to one more department using the same structure | Two departments running well beats eight running badly. | Not started
23 | Weeks 10 to 13: decide | Schedule the policy and tool list review for 90 days out | The landscape moves faster than your handbook does. | Not started

## Progress
Section | Done | Applicable | Complete
Weeks 1 to 3: discover | 0 | 5 | 0%
Weeks 4 to 6: govern | 0 | 6 | 0%
Weeks 7 to 9: pilot | 0 | 6 | 0%
Weeks 10 to 13: decide | 0 | 6 | 0%
TOTAL | 0 | 23 | 0%