## Start Here
MSP Transition Plan
AEGITz ¦ Phoenix's Business Resilience Partner ¦ aegitz.com
What this is for
Changing IT providers without a bad month. Most of this happens before anyone gives notice, which is the part companies skip. Run the ownership audit even if you have no intention of leaving. Knowing you could is worth having.
How to use it
1. Work top to bottom on the Checklist tab. The order is deliberate.
2. Set Status on each line. The Progress tab totals as you go.
3. Put a real name in Owner. Unowned items do not get done.
4. Anything you mark N/A gets a reason in the Notes column.
Legend
Shaded cells are the ones you fill in.
Status options: Not started, In progress, Done, N/A.
This workbook is provided free by AEGITz. It is operational guidance, not legal advice. Have counsel review anything you adopt that carries a regulatory obligation.

## Checklist
# | Section | Task | Why it matters / how to do it | Status | Owner | Due | Notes
1 | Before you give notice | Confirm your domain registration is in your company name | The single most disruptive thing to recover after a bad exit. Fix it while the relationship is friendly. | Not started
2 | Before you give notice | Confirm you control DNS | Registrar and DNS host may be different. You need both. | Not started
3 | Before you give notice | Confirm the Microsoft or Google tenant is owned by your company | Not by the provider's partner tenant with you as a customer object. | Not started
4 | Before you give notice | Confirm line of business software licenses are in your name | Licenses purchased under a provider agreement may not transfer and may need repurchasing. | Not started
5 | Before you give notice | Confirm you own and can access your backup data | Including whether the data is exportable in a usable format and how long export takes. | Not started
6 | Before you give notice | Confirm ownership of phone numbers and any SIP trunking | Porting takes time and cannot be rushed at cutover. | Not started
7 | Before you give notice | Create a break-glass admin account in your own tenant | Credentials in a safe, not shared with any provider. Standard practice regardless of whether you are switching. | Not started
8 | Before you give notice | Request current documentation as part of a normal review | Network diagram, asset inventory, license list, vendor accounts. Hesitation here tells you to plan for a harder exit. | Not started
9 | Before you give notice | Read the contract for term, notice period, and auto-renewal | Note the date by which notice must be given, and whether offboarding is included or billable. | Not started
10 | Selecting the replacement | Score candidates and your incumbent with the 3AM Test scorecard | Compare rather than react. A better score is not automatically a better fit. | Not started
11 | Selecting the replacement | Confirm experience with your core line of business application | The generalist who has never seen your practice management system will learn on your time. | Not started
12 | Selecting the replacement | Ask each candidate to describe onboarding for a company your size, with a timeline | Vagueness here predicts vagueness later. | Not started
13 | Selecting the replacement | Ask what they learned from a transition that went badly | Everyone has had one. The ones who say otherwise are the concern. | Not started
14 | Selecting the replacement | Ask what they do if the outgoing provider does not cooperate | Uncooperative transitions are common and an experienced provider has a playbook. | Not started
15 | Selecting the replacement | Check references from a client who left them | More informative than a happy current client. | Not started
16 | Week 1: discovery and access | New provider documents the environment independently | Do not rely on the handover being complete or accurate. | Not started
17 | Week 1: discovery and access | Deploy new monitoring and management agents alongside the incumbent's | Safe to run in parallel and it starts the learning immediately. | Not started
18 | Week 1: discovery and access | Identify license ownership issues | Find this in week one, not on the last day. | Not started
19 | Week 1: discovery and access | Build the credential inventory for rotation | Everything the outgoing provider's technicians could reach. | Not started
20 | Week 2: parallel operations | Both providers have visibility, incumbent still responsible | Gaps in the documentation surface here, while there is still someone to ask. | Not started
21 | Week 2: parallel operations | Ask the outgoing team directly about undocumented workarounds | Politely and early. Most technicians are professionals who like their work and will tell you. | Not started
22 | Week 2: parallel operations | Verify backups under the new configuration | Overlap the old and new backup deliberately. Pay for the extra month. | Not started
23 | Week 2: parallel operations | Communicate the change to staff with dates and new contact details | More than once, through more than one channel. | Not started
24 | Week 3: cutover | Move support routing to the new provider | New phone number and email, announced again on the day. | Not started
25 | Week 3: cutover | Rotate administrative account credentials | Security requirement, not a comment on anyone's character. | Not started
26 | Week 3: cutover | Rotate service accounts, network device passwords, and wifi keys | Work the credential inventory line by line. | Not started
27 | Week 3: cutover | Rotate API keys and integration credentials | Including anything held in the outgoing provider's documentation platform. | Not started
28 | Week 3: cutover | Transfer or re-establish vendor relationships | ISP, phone carrier, hardware vendors, software support contracts. | Not started
29 | Week 4: cleanup and verification | Remove the outgoing provider's agents, tools, and remote access software | Then verify independently. Orphaned remote access phoning home is the most common leftover. | Not started
30 | Week 4: cleanup and verification | Disable the outgoing provider's accounts in your systems | Including guest accounts and any partner delegated administration relationship. | Not started
31 | Week 4: cleanup and verification | Run an independent scan to confirm nothing was left behind | Trust but verify, and document the verification. | Not started
32 | Week 4: cleanup and verification | Test a restore under the new configuration | Not a backup report. A restore, with the elapsed time written down. | Not started
33 | Week 4: cleanup and verification | Confirm documentation handover is complete | Against the list you requested before giving notice. | Not started
34 | Week 4: cleanup and verification | Close out the final invoice and the relationship | Pay it. Phoenix is smaller than it looks, and you may need one password nobody wrote down. | Not started

## Progress
Section | Done | Applicable | Complete
Before you give notice | 0 | 9 | 0%
Selecting the replacement | 0 | 6 | 0%
Week 1: discovery and access | 0 | 4 | 0%
Week 2: parallel operations | 0 | 4 | 0%
Week 3: cutover | 0 | 5 | 0%
Week 4: cleanup and verification | 0 | 6 | 0%
TOTAL | 0 | 34 | 0%